## Sheet1
Task name | Category | Task description | Opening date | Owner | Priority | Closing date | Notes
Fix collision resistant hash. | Design Issue | 1)CollisionResistantHash interface should be renamed CryptographicHash | 2011-11-01 | Yael |  |  | Possible categories are:
|  | 2) TargetCollisionResistant interface will be deleted. Therefore CryptographicHash will become the root of the family |  |  |  |  | · Bug Fix
|  | 3) Add a new category of SecurityLevel: HashSecLevel<-TargetCollisionResistant<-CollisionResistant |  |  |  |  | · Design Bug Fix
|  | 4) All the SHA algorithms implemented in SCAPI are CollisionResistant. |  |  |  |  | · New Feature
Review Tapdoor permutation init functions | Design Issue | Check why we need init that accepts public, private key and params for, since in all our implementations we throw exceptions if called. If thought for future use, then specify in SDD | 2011-11-02 | Yael |  |  | · Design Issue
Add get coordinates functions to dlog GroupElement | New Feature | 1)Add getPointCoordinates function to ECPoint classes | 2011-11-02 | Moriya |  | 2011-11-06 | · Future task
|  | 2)Add getValue function to ZpElement class |  |  |  |  | ·
|  | 3)Add the function getPoint to the ECPoint interface (it is already implemented in the concrete classes) |  |  |  |  | Owner: The person responsible for solving task.
Add the functionality of point at infinity to the ECDlog groups | New Feature | 1)Add a boolean to ECPoint that indicates if this point is the infinity | 2011-11-02 | Moriya |  | 2011-12-05
|  | 2)Add the functionality of the infinity point to the functions that operate the points calculations –multiply, exponentiate, inverse, etc. |  |  |  |  | Priority:
Garbled circuits | Future tasks | This supposedly does "garbled circuits" in Java. We will need to do this after the library is ready (it will probably be one of the first tasks). If we can use their system, this can save us a lot of work. They also put a lot of effort into optimizations… | 2011-11-02 |  |  |  | · Very Low
· Low
|  | http://mightbeevil.org/framework/download.html |  |  |  |  | · Regular
· High Priority
· Urgent
Change name of JavaInterface.dll | Design Issue | Change name to CryptoPPJavaInterface.dll | 2011-11-02 | Moriya |  | 2011-12-05
Add getElement() to GroupElements | New Feature | 1)To ZpElement intfc add BigInteger getElement() | 2011-11-02 | Moriya |  | 2011-11-06
2) To EcElement intfc add some functionality
Make getPoint function package private | Design Bug Fix | And every other function that is only called by the respective Dlog group in the package | 2011-11-03 | Moriya |  | 2011-11-06
Rename the Dlog groups we have right now as DlogZpSafePrime and make it inherit from DlogZp and mark it as DDHSecure |  | In constructor of group check that p = 2q+1 |  | Moriya |  | 2011-11-08
Add to SRS documentation that we need to write a DlogZp that is general
Add to dloggroupsafeprime a constructor that receives the length of p and chooses a random safe prime p and finds the g |  |  |  | Moriya |  | 2011-11-08
Bug: ZpGroupParams need to check that p = 2q + 1 and then check primality for both |  |  | 2011-11-07 | Moriya |  | 2011-11-07
In Function createDlogZp |  |  | 2011-11-07 | Moriya |  | 2011-11-07
In DlogGroup.cpp of JNI change the name of the argument “element” to “possibleGenerator”
PointerToGroup is a member variable of CryptoPPDlogZp. It shouldn’t start with capital |  |  | 2011-11-07 | Moriya |  | 2011-11-07
Make all mathematical operations in that don’t involve a specific instance in DlogGroup static.
SecurityLevel |  | 1)Add SecurityLevel hierarchy to SCAPI project. There will be a new package edu.biu.scapi.securityLevel | 2011-11-07 | Yael
2)Mark all algorithms with corresponding security level
Change package names that have more than one word to standard lowerUpperCase |  |  | 2011-11-07 | Yael
Fix NtlJavaInterface functions according to the change of PerfectUniversalHash package name | Bug Fix | Change the signatures of the function according to the change of the package PerfectUniversalHash to perfectUniversalHash | 2011-11-08
SCAPI has to provide a tool for creating a default symmetric/asymmetric encryption | Design issue | May be there will be a concrete class for each of these families that gets the default parameters from some file and calls constructors as necessary. Or some other solution. | 2011-12-04 | Yael | regular
In First Layer SDD: in abstract classes paragraph add note that if the abs class has only one function with one line or so, then it is not necessary to have. |  | In First Layer SDD: in abstract classes paragraph add note that if the abs class has only one function with one line or so, then it is not necessary to have. | 2011-12-14 | Yael | regular
add implementations for getEncoded() and getFormat() functions of ScRabinPublic/PrivateKey | Bug Fix |  | 2011-12-26
add the missing test vectors |  | The classes that don't have test vectors are DlogZpTest and DlogEcF2mTest | 2011-12-26
Mapping binary string to dlog group | New Feature | 1) Add function convertStringToGroupElement(String str) : GroupElement to general DlogGroup interface. | 2011-12-14 | Yael | High | 2011-12-27
2) Add function convertByteArrayToGroupElement(Byte[] binaryString) : GroupElement
Each implementing class has to implement this because the group element is different and the way to obtain it is different
fix 1st layer SDD to have key generation for not widely used algorithms |  | add key generation for algorithms such as - LubyRackoffPrpFromPrfVarying, IteratedPrfVarying, etc. | 2012-01-01
implement key generation for not widely used algorithms | New Feature |  | 2012-01-01 |  | high
change Rabin keys to implements KeySpec interface instead of Key | Design Bug Fix |  | 2012-01-01 |  | high
delete getSecretKey functions from primitives layer | Bug Fix |  | 2012-01-02 | moriya | high | 2012-01-04
change getAlgorithmName function in the primitives layer | Design Bug Fix | add concatenation of the underlying algorithm name (if there is one) | 2012-01-03 |  | high
in HKDF constructor that gets a hmac name - add a check that the given name is indeed a hmac name | Bug Fix |  | 2012-01-03
In First Layer SDD: reconsider the PRF section | Design Issue | 1. think may be we want to put the compute block without lengths in the PRP interface and the computeBlock with inut length in the PrfVaryingInputLength instead of in the main PRF interface | 2012-01-23
2. currently we have getBlockSize function in PRF. May be we want to change it to getInputSize and getOutputSize
Init Exceptions | Design Issue | We should have a new exception called InitializationException that is thrown whenever the init function doesn't succeed. It collects the actual reason or exception why it didn't succeed and puts that as the message of the exception. | 2012-02-09 | Yael | High
Dlog group-- isIdentity() | New Feature | Add a new function to DlogGroup interface: boolean isIdentity(GroupElement gEl) | 2012-02-09 | Yael | High
Dlog group-- source of randomness | Bug Fix | Where should DlogGroup get the source of randomness from. At the moment, creates whenever needed new SecureRandom | 2012-02-09 | Yael | High
DlogGroup-simultaneous exponentiations | Bug Fix | This is not really a bug. At the moment we have implemented this function in a naïve way, without the optimization suggested in the book of applied crypto. See if we can optimize. | 2012-02-20 | Yael | High
DlogGroup - init functions | Design Issue | 1. delete the init functions that gets a strings from elliptic curve classes. The init function that gets an algorithmParameterSpec does the same things. | 2012-02-26 | moriya | high
2. dlogZp - add a class DlogZpRandomParams that hold the numOfBits.
3. dlogZp - delete the init function that gets numOfBits. Instead, the init function that gets the algorithmParameterSpec can get an instance of DlogZpRandomParams. IN this case this init function will act the same as the init that gets the numOfBits.
TrapdoorPermutation - init functions | Design Issue | 1. delete the init function that gets algorithmParameterSpec.
2. add aclass KeyPairGenerator that gets the name of an algorithm and return a pair of keys to this algorithm. In case the name is Rabin - generate key pair using CryptoPpJavaInterface dll.
3. the init function that gets the keys and an algorithmParameterSpec shouldn't throw an excetion, but ignore the params, as we did in other primitive families.